## Project Overview
Time spent(h)
Iteration | Andrew | Jimmy | Linda | Sofia | Total
0 | 6.5 | 9 | 0 | 9.5 | 25
1 | 15.5 | 15.75 | 20.75 | 14.25 | 66.25
2 | 20 | 20.75 | 13.5 | 27 | 81.25
3 | 22.5 | 23.5 | 33.25 | 23.25 | 102.5
4 | 21 | 26 | 22.5 | 26.75 | 96.25
5 | 20 | 20 | 19 | 28.25 | 87.25
6 | 20.5 | 26.25 | 15 | 25.75 | 87.5
7 | 20.5 | 29.5 | 20 | 17.5 | 87.5
8 | 19.5 | 25.5 | 27.5 | 23 | 95.5
9 | 12.5 | 10.5 | 13.5 | 11 | 47.5
10 |  |  |  |  | 0
Total | 178.5 | 206.75 | 185 | 206.25 | 776.5

## Andrew Ind
Iteration | Requirement | Task | Status | Estimate | Actual
0 | Lecture | Watch introduction | Done | 1.75 | 1
| Group meeting | Distribute tasks, decide on roles | Done | 1 | 1
| Post mortem | Read at least one post mortem from previous years | Started | 2 | 1
| Customer Contact | Initiate contact | Done | 1 | 1
| Time report | Write for the first week | Started | 1 | 1
| Tutor Meeting | Send three potential times for the weekly meetings | Done | 1 | 1
| Requirements | Begin defining requirements | Started | 2 | 0.5
|  |  | Sum | 9.75 | 6,5
|  |  | Time since previous iteration |  | 0
|  |  | Time total in the project |  | 6,5
1 | Requirement | Task | Status | Estimate | Actual
| Group meeting | Distribute tasks, decide on roles | Done | 2 | 2
| Tutor Meeting | Present the work done during week | Done | 1 | 0.5
| Customer Contact | Meeting with developer | Done | 1 | 1
| Time report | Write for the iteration 1 | Done | 1 | 1
| Requirements | Defining requirement | Done | 4 | 4
| Vision Document | Write vision document | Done | 2 | 2
| Version Control | Investigate version control | Done | 1 | 1
| SignalR POC | Initial check for suitability | Done | 4 | 4
|  |  | Sum | 15 | 15.5
|  |  | Time since previous iteration |  | 6.5
|  |  | Time total in the project |  | 21.5
2 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 2 | Done | 0.5 | 1
| Tutor meeting | Present the work done during iteration 1 | Done | 1 | 0.5
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 1 | 0.5
| Group meeting | See how everyone is doing, quick update | Done | 0.5 | 0.5
| Customer | Customer communication | Done | 1 | 1
| Product Backlog | Update PB with regards to customer's clarifications | Done | 1 | 1
| Encryption | Signal Encryption POC technical assessment | Started | 3 | 2
| Encryption | Signal Encryption code start | Abandoned | 5 | 2
| Server Auth API | Write auth code for server api | Started | 15 | 8
| API Tests | Write postman tests and docs for api | Started | 5 | 3
| Time report | Write for iteration 3 | Started | 1 | 0.5
|  |  | Sum | 34 | 20
|  |  | Time since previous iteration |  | 21.5
|  |  | Time total in the project |  | 41.5
3 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 3 | Done | 0.5 | 0.5
| Tutor meeting | Present the work done during iteration 2 | Done | 1 | 1
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5 | 0.5
| Customer | Delivery | Done | 1 | 2.5
| Deliverable Feedback | Give feedback on other group's documentation | Done | 1 | 2.5
| F1 User text message | Server text message functionality | Started | 7 | 3
| F2 User login | Write code for server api login | Done | 1 | 1
| F3 User own data access | User can get information about themselves | Done | 2 | 4
| F4 Add friends | User can add friends | Done | 2 | 4
| API Tests | Write postman tests and docs for api | Started | 5 | 2
| Azure install | Setup Azure and contuous delivery from repo. | Started | 2 | 1
| Time report | Write for iteration 4 | Started | 0.5 | 0.5
|  |  | Sum | 23.5 | 22.5
|  |  | Time since previous iteration |  | 41.5
|  |  | Time total in the project |  | 64
4 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 4 | Done | 0.5 | 0.5
| Tutor meeting | Present the work done during iteration 3 | Done | 1 | 1
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5 | 0.5
| Customer | Delivery | Done | 1 | 0.5
| Presentation | Attend project presentation | Done | 1 | 1
| F1-F4 | Fix bugs and update login flows | Done | 6 | 8
| F1-F4 API Tests | Write postman tests and docs for api | Done | 5 | 5
| F5 | Research into F5, SignalR wiki docs | Done | 3 | 3
| Azure fixes | Adjust delivery flow to cope with database changes | Done | 0 | 1
| Time report | Write for iteration 5 | Not started | 1 | 0.5
|  |  | Sum | 19 | 21
|  |  | Time since previous iteration |  | 64
|  |  | Time total in the project |  | 85
5 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 5 | Done | 0.5 | 0.5
| Tutor meeting | Present the work done during iteration 4 | Done | 1 | 1
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5 | 0.5
| Customer | Delivery | Done | 1 | 0.5
| F5/F6 | Write server code for group chat | Done | 12 | 13
| Server Testing | Initiate xUnit testing framework | Done | 0 | 2
| Elaboration docs | Update elaboration documentation | Done | 1 | 1
| Azure fixes | Fix deploy to Azure | Done | 0 | 1
| Time report | Write for iteration 6 | Started | 1 | 0.5
|  |  | Sum | 17.5 | 20
|  |  | Time since previous iteration |  | 85
|  |  | Time total in the project |  | 105
6 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 6 | Done | 0.5 | 0.5
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5 | 0.5
| Group documentation | Move time reports, milestones | Done | 0 | 2
| F5/F6 | Refactor/improve/test server code for group chat | Started | 12 | 6
| Server Testing | Elaborate xUnit testing framework | Not started | 4 | 0
| F1 | Improving aspects of F1, take care of existing issues | Done | 0 | 6
| Elaboration feedback | Read other group's elaboration and comment | Done | 2 | 3
| Elaboration presentation | Prepare elaboration presentation | Done | 1 | 2
| Time report | Write for iteration 7 | Started | 0.5 | 0.5
|  |  | Sum | 20.5 | 20.5
|  |  | Time since previous iteration |  | 105
|  |  | Time total in the project |  | 125.5
7 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 7 | Done | 0.5 | 0.5
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5 | 0.5
| Group documentation | Time reports, milestones, iteration summary | Done | 2 | 2
| Customer Meeting | Delivery | Done | 1 | 1
| F5/F6 | Refactor/improve/test server code for group chat | Started | 6 | 6
| Issues | Take care of existing issues | Done | 4 | 5
| U2 | Create WCAG spreadsheet, read docs | Started | 10 | 5
| Time report | Write for iteration 8 | Started | 0.5 | 0.5
|  |  | Sum | 24.5 | 20.5
|  |  | Time since previous iteration |  | 125.5
|  |  | Time total in the project |  | 146
8 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 8 | Not started | 0.5 | 0.5
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5 | 0.5
| Group documentation | Move time reports, milestones | Done | 2 | 2
| Tutor meeting | Tutor meeting | Done | 0.5 | 0.5
| F5/F6 | Update user details, password | Done | 8 | 8
| Server Testing | Write tests for adding, deleting, user details etc. | Started | 6 | 4
| Update docs | Update documentation ahead of handin | Done | 4 | 4
| Time report | Write for iteration 9 | Not started | 0.5 | 0
|  |  | Sum | 22 | 19.5
|  |  | Time since previous iteration |  | 146
|  |  | Time total in the project |  | 165.5
9 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 9 | Not started | 0.5 | 0.5
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Not started | 0.5 | 0
| Tutor meeting | Tutor meeting | Not started | 0.5 | 0.5
| WCAG | Test WCAG and update code accordingly | Not started | 8 | 0
| Server Testing | Write tests for adding, deleting, user details etc | Started | 2 | 0
| Construction feedback | Give other group construction feedback | Not started | 4 | 3
| Load testing | Server load testing | Not started | 4 | 3
| SignalR testing | Writing tests for SignalR | Started | 0 | 2
| Presentation | Writing presentation for product | Done | 0 | 3
| Time report | Write for iteration 10 | Not started | 0.5 | 0.5
|  |  | Sum | 20 | 12.5
|  |  | Time since previous iteration |  | 165.5
|  |  | Time total in the project |  | 178
10 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 9 | Not started | 0.5 | 0
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Not started | 0.5 | 0
| Handover meeting | Hand over project. | Not started | 1 | 0
| Presentation Meeting | Present project | Not starter | 3 | 0
| WCAG | Test WCAG and update code accordingly | Not started | 4 | 0
| Documentation | Finish off documentation ahead of handover. | Not started | 3 | 0
| Server Testing | Write tests for adding, deleting, user details etc | Started | 4 | 0
| Load testing | Server load testing | Started | 4 | 0
| SignalR testing | Writing tests for SignalR | Started | 4 | 0
|  |  | Sum | 24 | 0
|  |  | Time since previous iteration |  | 178
|  |  | Time total in the project |  | 178

## Jimmy Ind
Iteration | Requirement | Task | Status | Estimate | Actual
0 | Lecture | Watch introduction | Done | 1.75 | 1
| Group meeting | Distribute tasks, decide on roles | Done | 1 | 0.5
| Post mortem | Read at least one post mortem from previous years, write down comments | Done | 2 | 1.5
| Github repo | Setup Github repo for the project | Done | 1.5 | 1
| Risk list | List and prioritize as many risks as possible | Done | 1 | 1.5
| Documentation | Diagrams | Started | 2 | 2
| Time report | Write for first week | Done | 1 | 0.75
| Iteration plan | Create for iteration 1 | Done | 1 | 0.75
|  |  | Sum | 11.25 | 9
|  |  | Time since previous iteration |  | 0
|  |  | Time total in the project |  | 9
1 | Requirement | Task | Status | Estimate | Actual
| Tutor meeting | Present the work done | Done | 1 | 0.5
| Group meeting | Distribute tasks & introduction for Linda | Done | 0.5 | 0.75
| Time report | Write for this week | Done | 1 | 1
| Group discussion | Discussion on slack | Started | 1.5 | 1
| Customer meeting | Meeting concerning tech implementation | Done | 1 | 0.75
| Github wiki | Update Home with correct links to pages | Done | 0.25 | 0.25
| Risk list | Update | Done | 3 | 1.5
| Product Backlog | Prioritize and add comments | Done | 2 | 1.5
| Github repo | Get info about Waffle.io | Done | 2 | 0.5
| Github repo | Investigate version control and create instruction | Done | 1.5 | 2.5
| Implementation | Investigate different techniques needed in the project | Done | 1 | 1
| Implementation | Initialize client | Done | 4 | 3.5
| Implementation | WebRTC POC - Start creating Proof of concept for video chat. Continue next iteration. | Done | 1 | 1
|  |  | Sum | 19.75 | 15.75
|  |  | Time since previous iteration |  | 9
|  |  | Time total in the project |  | 24.75
2 | Requirement | Task | Status | Estimate | Actual
| Tutor meeting | Present the work done | Done | 1 | 0.5
| Group meeting | Discuss latest iteration. Distribute tasks for next. | Done | 0.5 | 0.5
| Group meeting | Discussion | Done | 0.5 | 0.5
| Time report | Write for this week | Done | 1 | 0.5
| Product backlog | Prioritize | Done | 0.5 | 0.25
| Group communication | Discussion in Slack | Done | 1 | 0.5
| POC | Get info about WebRTC, SignalR and Azure. | Done | 5 | 4
| POC | WebRTC - Video chat | Done | 10 | 14
| Software architecture | Preliminary architecture for the project | Not started | 4 | -
|  |  | Sum | 24.5 | 20.75
|  |  | Time since previous iteration |  | 24.75
|  |  | Time total in the project |  | 45.5
3 | Requirement | Task | Status | Estimate | Actual
| Tutor meeting | Present the work done | Done | 1 | 0.75
| Group meeting | Distribute tasks | Done | 0.5 | 0.75
| Group meeting | Discuss tutor meeting | Done | 0.25 | 0.25
| Group meeting | Discuss customer meeting | Done | 0.25 | 0.25
| Group discussion | Discussion on slack | Done | 2 | 1.25
| Time report | Write for this week | Done | 1 | 1
| Customer meeting | Meeting with the customer | Done | 1 | 0.75
| Peer review | Review Group 2 | Done | 3 | 2.5
| Peer review | Read review from group 0 | Done | 0.5 | 0.5
| Customer meeting | Get info about Azure-account before customer meeting | Done | 0.5 | 0.5
| Software architecture | Preliminary architecture for the project | Done | 5 | 5.25
| F1 User Register | Start implement register functionality for client and setup Material-ui. Continue next iteration with requests to server. | Done | 5 | 6
| F2 User login | Start implement login functionality for client. Continue next iteration with requests to server. | Done | 3 | 3.75
|  |  | Sum | 23 | 23.5
|  |  | Time since previous iteration |  | 45.5
|  |  | Time total in the project |  | 69
4 | Requirement | Task | Status | Estimate | Actual
| Tutor meeting | Present the work done | Done | 0.75 | 0.5
| Group meeting | Distribute tasks | Done | 0.75 | 0.75
| Group meeting | Discuss tutor meeting | Done | 0.25 | 0.5
| Group meeting | Discuss customer meeting | Not started | 0.25 | -
| Customer meeting | Meeting with the customer | Not started | 0.75 | -
| Group discussion | Discussion on slack | Done | 2 | 1.25
| Peer review | Attend presentation of Inception by all groups | Done | 1 | 1
| Time report | Write for this week | Done | 1 | 0.75
| Technical documentation | Update | Done | 1.5 | 1.5
| Risk list | Update with technical risks | Done | 1 | 0.75
| Azure setup | Setup Azure automatic deployment from repo. | Done | 2 | 2
| Azure setup | Trying to fix issues with database on Azure. | Done | 1 | 2
| F1 User Register | Add API-requests. | Done | 2 | 4.25
| F2 User login | Add API-requests. | Done | 2 | 2
| F3 User own data access | Client: User can get information about themselves | Done | 3 | 5
| F4 Add friends | Client: User can add friends | Done | 6 | 3.75
|  |  | Sum | 25.25 | 26
|  |  | Time since previous iteration |  | 69
|  |  | Time total in the project |  | 95
5 | Requirement | Task | Status | Estimate | Actual
| Group meeting | Discuss customer meeting | Done | 0.25 | 0.5
| Customer meeting | Meeting with the customer | Done | 0.75 | 0.25
| Group discussion | Discussion on slack | Done | 2 | 0.75
| Technical documentation | Explain WebRTC and create diagrams. | Done | 2 | 2.5
| Azure setup | Fix Azure problems. Setup new Azure webapps and automatic deployment from Github. | Done | 0 | 2
| F1-F4 | Client: Fix bugs and refactor. Also add layouts for screen breakpoints. | Done | 6 | 9.75
| F5 User chat room | Start implement on client. Continue next iteration. | Done | 5 | 3.75
| Time report | Write for this week | Done | 1 | 0.5
|  |  | Sum | 17 | 20
|  |  | Time since previous iteration |  | 95
|  |  | Time total in the project |  | 115
6 | Requirement | Task | Status | Estimate | Actual
| Group meeting | Discuss latest iteration. Distribute tasks for next. | Done | 0.5 | 0.5
| Group discussion | Discussion on slack | Done | 2 | 0.75
| Peer review | Attend presentation of Elaboration by all groups | Done | 1 | 1
| Perr Review | Review Meridium-group elaboration | Done | 2 | 0.5
| F5 User chat room | Implement on client. Continue next iteration | Done | 5 | 7
| F6 User text message | Implement on client. Continue next iteration | Done | 5 | 4
| User Avatar bugs | Fix bugs for image upload | Done | 3 | 5.25
| Server Architecture | Update Diagrams | Done | 5 | 6
| Azure Setup | Fix issue with auto-deployment to Azure. Changed Azure-plan from free to basic. | Done | 0 | 0.75
| Time report | Write for this week | Done | 1 | 0.5
|  |  | Sum | 24.5 | 26.25
|  |  | Time since previous iteration |  | 115
|  |  | Time total in the project |  | 141.25
7 | Requirement | Task | Status | Estimate | Actual
| Tutor meeting | Present the work done | Done | 0.75 | 0.25
| Group meeting | Discuss tutor meeting | Done | 0.25 | 0.25
| Group meeting | Discuss latest iteration. Distribute tasks for next. | Done | 0.5 | 0.5
| Group discussion | Discussion on slack | Done | 2 | 1
| Group meeting | Discuss customer meeting | Done | 0.25 | 0.25
| Customer meeting | Meeting with the customer | Done | 0.75 | 0.5
| F5 User chat room | Implement on client. | Done | 5 | 5
| F6-F7 User text message | Implement on client. | Done | 7 | 6
| F10 Video Call | Implement Video call. | Done | 8 | 12.25
| F1-F10 Bug Fix | Fix discovered bugs and update css. Continue next iteration. | Done | 1 | 3
| Time report | Write for this week | Done | 1 | 0.5
|  |  | Sum | 26.5 | 29.5
|  |  | Time since previous iteration |  | 141.25
|  |  | Time total in the project |  | 170.75
8 | Requirement | Task | Status | Estimate | Actual
| Tutor meeting | Present the work done | Done | 0.5 | 0.25
| Group meeting | Discuss tutor meeting | Done | 0.25 | 0.25
| Group discussion | Discussion on slack | Done | 2 | 1.5
| F1-F13 Bug Fix | Fix discovered bugs and update css. | Done | 15 | 16
| F5-F6 | Add change password and user details on client. | Done | 2 | 3
| Documentation | Update technical documentation, diagrams and clients README.md | Done | 3 | 4
| Time report | Write for this week | Done | 0.5 | 0.25
|  |  | Sum | 23.25 | 25.5
|  |  | Time since previous iteration |  | 170.75
|  |  | Time total in the project |  | 196.25
9 | Requirement | Task | Status | Estimate | Actual
| Tutor meeting | Present the work done | Done | 0.5 | 0.25
| Group meeting | Discuss tutor meeting | Done | 0.25 | 0.25
| Group meeting | Discuss latest iteration. Distribute tasks for next. | Done | 0.5 | 0.5
| Group discussion | Discussion on slack | Done | 2 | 0.75
| F1-F13 Bug Fix | Fix discovered bugs and update css. | Done | 10 | 6.5
| Group documentation | Move time reports. Analysis of Iteration 8 | Done | 2 | 2
| Time report | Write for this week | Done | 0.5 | 0.25
|  |  | Sum | 15.75 | 10.5
|  |  | Time since previous iteration |  | 196.25
|  |  | Time total in the project |  | 206.75

## Linda Ind
Iteration | Requirement | Task | Status | Estimate | Actual
1 | Tutor meeting | Present the work done | Done | 0.5 | 0.5
| Group meeting | Introduction and catch up | Done | 0.5 | 0.25
| Documentation | Research update order of pages | Done | 0.5 | 0.5
| Client communication | Get information on requirements for app | Done | 0.5 | 0.5
| Group meeting | Deciding what to do until next meeting | Done | 0.25 | 0.25
| Documentation | Update time report | Done | 0.5 | 0.5
| Lecture | Watch course introduction | Done | 1.75 | 1.5
| Project knowledge | Read through entire course page | Done | 1 | 2
| Documentation | Update time report | Done | 0.5 | 0.5
| Project knowledge | Read requirements document for application, from customer RedRiver | Done | 0.5 | 0.25
| Documentation | Catch up on project documentation so far, discuss with group, make changes | Done | 1.5 | 1.5
| Project knowledge | Go through GitHub repository | Done | 1 | 0.25
| Group communication | Discuss with group on Slack on what to do during the day | Done | 0.25 | 0.25
| Client communication | Send e-mail to client RedRiver/Mattias regarding Mobile BankID | Done | 0.5 | 0.5
| Client communication | Add document to repository with questions to client RedRiver, regarding requirements | Done | 1 | 2
| Group communication | Discuss requirements with group on Slack | Done | 0.5 | 0.5
| Documentation | Update time report | Done | 0.25 | 0.25
| Project knowledge | Research SignalR, WebRTC and techniques for live streaming. Discuss with group on Slack. | Done | 1 | 1.25
| Documentation | Read through product backlog, flag requirements that need to be made clearer or divided up. Chat about project with group on Slack. | Done | 1.5 | 2.25
| Documentation | Read through product backlog, flag requirements. Double check requirements document and notes from meeting with client. Add new functionality and reliability requirements to product backlog. Post questions to group on Slack. | Done | 1 | 1.5
| Client communication | Update questions file and add more questions | Done | 0.5 | 1.25
| Client communication | Add updated questions file to repository | Done | 0.5 | 0.5
| Documentation | Read through updated Vision document, add new updates, post questions on Slack to group members about Vision document and requirements. | Done | 0.5 | 0.5
| Post Mortem | Read one post mortem from previous years | Done | 2 | 1.5
|  |  | Sum | 18.5 | 20.75
|  |  | Time since previous iteration | 18.5 | 20.75
|  |  | Time total in the project | 18.5 | 21
2 | Requirement | Task | Status | Estimate | Actual
| Application interface | Set up collaborative diagram in Draw.io, test exporting clickable prototype in HTML, send invitation email to group members | Done | 1 | 2.25
| Tutor meeting | Present the work done | Done | 0.5 | 0.5
| Group meeting | Discussion on what to do next | Done | 0.25 | 0.25
| Documentation | Chat with group on Slack about requirements, go through answers from RedRiver, update product backlog | Done | 2 | 2
| Documentation | Update test specification, add test cases | Done | 1 | 1.75
| Documentation | Add new questions to RedRiver in question file, upload question file | Done | 0.5 | 0.5
| Group communication | Chat with group members on Slack about encryption, product backlog comments and what to bring up with client via mail/meeting | Done | 0.25 | 0.25
| Peer Review - Inception | Read on course page what should be in peer review, chat on Slack with group members to make sure everything is included. Update test specification for peer review. | Done | 0.5 | 0.75
| Documentation | Update project plan | Done | 0.25 | 0.25
| Documentation | Update test specifikation with new manual test cases. | Done | 0.25 | 0.25
| Peer Review - Inception | Chat with group members on Slack about documents needed for peer review. | Done | 0.25 | 0.25
| Documentation | Update test specifikation, change enumeration on manual test cases to increase traceability between requirements in product backlog and manual test cases in test specification. | Done | 0.25 | 0.25
| Documentation | Update time report | Done | 0.5 | 0.5
| Project knowledge | Write plan for next week as project manager. Add new document in Wiki for iteration 3. Update project plan. Discuss project plan on Slack with group members. Discuss with previous project manager (Sofia) about routines for time reporting and analysis of previous week. | Done | 2 | 2.25
| Documentation | Update time report, add to iteration 2, plan iteration 3 | Done | 0.5 | 1.5
| Peer review | Answer protocol questions for peer review | Not Started | 1 | 0
| Project knowledge | Read through WCAG 2.1 | Not Started | 1 | 0
| Documentation | Update test specifikation, add manual test cases. | Not Started | 7 | 0
| Group communication | Decide on breakpoints and devices to target | Not Started | 0.5 | 0
| Application interface | Set up simple mockups | Not Started | 0.5 | 0
|  |  | Sum | 20 | 13.5
|  |  | Time since previous iteration | 18.5 | 20.75
|  |  | Time total in the project | 38.5 | 34.25
3 | Requirement | Task | Status | Estimate | Actual
| Documentation | Put together time reports for group, update page "Iteration 2" with time report for iteration 2 | Done | 2 | 3
| Peer review | Add google docs document for peer review, send link to RedRiver group | Done | 2 | 0.5
| Group communication | Prepare for group meeting | Done | 0.5 | 0.5
| Group communication | Group meeting on Slack | Done | 0.5 | 0.75
| Group communication | Discussion on what to do next on Slack | Done | 0.25 | 0.25
| Group communication | Small update on what I'm doing to group members on Slack | Done | 0.25 | 0.25
| Project knowledge | Research Material-UI | Done | 0.25 | 0.25
| Group communication | Write protocol for group meeting | Done | 0.5 | 1.5
| Tutor meeting | Go through iteration plan for week, check time report, discuss risks, talk about possible problems | Done | 0.5 | 0.75
| Group meeting | Discuss project | Done | 0.5 | 0.25
| Client meeting | Write down questions to RedRiver to bring up at meeting | Done | 0.5 | 0.75
| Client meeting | Set up video call to RedRiver | Abandoned | 0.5 | 0.25
| Client meeting | Send link to video call to RedRiver | Done | 0.25 | 0.25
| Client meeting | Meeting at Google Hangouts with RedRiver | Done | 0.5 | 0.5
| Group meeting | Discuss project | Done | 0.25 | 0.25
| Documentation | Update time report, plan for iteration 3 (for group) | Done | 1 | 0.5
| Peer review | Add my own peer review to group document | Done | 2 | 3.5
| Peer review | Put together protocol for peer review | Done | 2 | 4.5
| Slack | Chat about peer review and project | Done | 0.25 | 0.25
| Peer review | Send protocol for peer review to Meridium group | Done | 0.5 | 0.25
| Planning | Write list on what needs to be done in project | Done | 0.5 | 0.75
| Documentation | Update time report, plan for iteration 3 (for group) | Done | 1 | 2
| Slack | Chat about how to handle project tasks | Done | 0.25 | 0.5
| Documentation | Update my own time report for iteration 3 | Done | 1 | 1.5
| Documentation | Add dependencies to product backlog | Done | 1 | 1
| Slack | Chat on Slack about project | Done | 0.25 | 0.5
| Peer review | Look at when material should be sent to course management | Done | 0.25 | 0.25
| Slack | Chat on Slack about customer delivery for week 15 | Done | 0.25 | 0.25
| F1, F2, F3, F4 | Update prototypes for customer delivery | Done | 3 | 4.25
| Slack | Chat on Slack about project | Done | 0.25 | 0.25
| Peer review | Read peer review from group Futurum | Done | 0.25 | 0.25
| Presentation Inception | Read Sofia's presentation | Done | 0.5 | 1.25
| Peer review | Read peer review from group Futurum, make bullet list of needed changes | Done | 1 | 1.5
| Documentation | Update test specification, add manual test cases. | Not Started | 4 | 0
|  |  | Sum | 28.5 | 33.25
|  |  | Time since previous iteration | 38.5 | 34.25
|  |  | Time total in the project | 67 | 67.5
4 | Requirement | Task | Status | Estimate | Actual
| Slack | Chat on Slack about project | Done | 0.5 | 0.5
| Client communication | E-mail questions to RedRiver | Done | 0.5 | 0.5
| Slack | Chat on Slack about project | Done | 0.5 | 0.75
| Documentation | Update my own time report for iteration 3 | Done | 1 | 1.5
| Slack | Chat on Slack about testing and peer review, changes needed in documentation | Done | 0.5 | 0.75
| Group communication | Weekly group meeting on Slack | Done | 0.75 | 0.75
| Tutor meeting | Go through iteration plan for week, check time report, discuss risks, talk about possible problems | Done | 0.5 | 0.5
| Slack | Chat on Slack about project | Done | 0.5 | 0.5
| Client communication | Send e-mail answer from RedRiver to group | Done | 0.25 | 0.25
| Client communication | E-mail new time for meeting to RedRiver | Done | 0.25 | 0.25
| Documentation | Write analysis of iteration 3, add to page for iteration 4 | Done | 1 | 2
| Peer review | Attend presentation of Inception done by Sofia | Done | 0.5 | 0.5
| Documentation | Summarize individual time reports for iteration 3 | Done | 3 | 3
| Documentation | Write iteration plan for iteration 4 (for group) | Done | 0.5 | 0.25
| Slack | Chat on Slack about registration form and what should be included | Done | 0.25 | 0.25
| Documentation | Write my own time report for iteration 4 | Done | 0.5 | 0.5
| Client communication | Write list of things to discuss with RedRiver | Done | 0.25 | 0.25
| Documentation | Add text for milestones M5 and M6, add text for deliverables | Done | 0.75 | 0.75
| F1 F2 F3 | Test system before meeting with RedRiver | Done | 0.25 | 0.25
| Peer review | Go through bullet list of needed changes from group Futurum, see if everything is updated | Done | 0.25 | 0.25
| Client communication | Start video call in Google Hangouts | Done | 0.25 | 0.25
| Client meeting | Meeting with RedRiver on Google Hangouts | Done | 0.5 | 0.5
| Slack | Chat on Slack about testing on different devices | Done | 0.5 | 0.5
| Peer review | Go through bullet list of needed changes from group Futurum, see if everything is updated | Done | 1 | 1
| Peer review | Prepare Wiki for being sent to course management, add information | Done | 1 | 2.75
| Peer review | Clone Wiki and send to course management | Done | 0.25 | 0.25
| Documentation | Update my own time report for iteration 4 | Done | 0.5 | 0.5
| Slack | Chat on Slack about test report and how it should be written | Done | 0.25 | 0.25
| Project knowledge | Refresh knowledge on React and JavaScript | Done | 1 | 2
| Documentation | Update my own time report for iteration 4 | Done | 0.5 | 0.25
|  |  | Sum | 18.25 | 22.5
|  |  | Time since previous iteration | 67 | 67.5
|  |  | Time total in the project | 85.25 | 90
5 | Requirement | Task | Status | Estimate | Actual
| Iteration plan | Plan iteration 5 | Done | 0.5 | 0.5
| Iteration plan | Write iteration plan for iteration 5 | Done | 0.5 | 0.5
| Time report | Update my own time report for iteration 4 | Done | 0.75 | 0.75
| Time report | Add my own time report for iteration 5 | Done | 0.25 | 0.25
| Time report | Write time report for entire group for iteration 4 | Done | 3 | 4.5
| Group communication | Weekly group meeting on Slack | Done | 0.5 | 1
| Tutor meeting | Go through iteration plan for week, check time report, discuss risks, talk about possible problems | Done | 0.5 | 0.25
| Slack | Discuss project | Done | 0.25 | 0.25
| Documentation | Summarize individual time reports for iteration 4 | Done | 3 | 4.5
| Time report | Update my own time report for iteration 5 | Done | 0.75 | 0.5
| Documentation | Write analysis of iteration 4, add to page for iteration 5 | Done | 1 | 0.5
| Slack | Read messages on Slack | Done | 0.5 | 0.75
| Slack | Chat on Slack about upcoming customer meeting | Done | 0.5 | 1
| Customer meeting | Start Google Hangouts video call for customer meeting, send link to customer | Done | 0.25 | 0.25
| Customer meeting | Discuss and show application | Done | 1 | 0.25
| Slack | Group meeting, discuss customer meeting and what to do next | Done | 0.5 | 0.5
| Slack | Chat about project, find emulators for device testing, found blisk.io | Done | 0.5 | 0.5
| Testing | Test application in browserstack | Done | 0.5 | 0.5
| Peer review | Go through Elaboration questions for peer review, write bullet list of things to fix | Done | 0.5 | 0.25
| Peer review | Prepare documentation for sending Elaboration material to group 0 | Done | 1 | 1
| Peer review | Clone down Wiki and repository | Done | 0.5 | 0.25
| Peer review | Send Wiki and repository to group 0 | Done | 0.5 | 0.25
| Project knowledge | Refresh knowledge on React and JavaScript | Not Started | 2 | 0
|  |  | Sum | 19.25 | 19
|  |  | Time since previous iteration | 85.25 | 90
|  |  | Time total in the project | 104.25 | 109
6 | Requirement | Task | Status | Estimate | Actual
| Time report | Update my own time report for iteration 5 | Done | 1 | 1
| Peer review | Read through group Meridium's Elaboration material | Done | 2 | 1
| Peer review | Read through peer review from other group | Done | 1 | 0.5
| Elaboration Presentation | Write presentation for Elaboration | Done | 4 | 6.75
| Elaboration Presentation | Find our peer review for presentation | Done | 0.25 | 0.25
| Elaboration Presentation | Write bullet list of our peer review for presentation | Done | 1 | 1.25
| Elaboration Presentation | Time presentation for Elaboration | Done | 0.25 | 0.25
| Elaboration Presentation | Transfer presentation manuscript to paper | Done | 1 | 2
| Elaboration Presentation | Hold presentation and peer review, listen to other groups | Done | 1 | 1
| WCAG 2.1 | Write bullet list of WCAG 2.1 | Started | 3 | 1
|  |  | Sum | 14.5 | 15
|  |  | Time since previous iteration | 104.25 | 109
|  |  | Time total in the project | 118.75 | 124
7 | Requirement | Task | Status | Estimate | Actual
| Time report | Update my own time report for iteration 6 | Done | 1 | 1
| Implementation | Clone repository, set up development environment | Done | 1 | 1
| Implementation | Build and run application, familiarize self with code in App.js | Done | 1 | 0.75
| Group meeting | Talk about project, divide tasks | Done | 0.5 | 0.5
| WCAG 2.1 | Write bullet list of WCAG 2.1 | Done | 5 | 8.75
| Tutor meeting | Talk about project, reports and presentation | Done | 0.25 | 0.25
| Group meeting | Talk about project, divide tasks | Done | 0.25 | 0.25
| WCAG 2.1 | Work on bullet list, send link to group | Done | 0.25 | 0.25
| Time report | Update my own time report for iteration 7 | Done | 0.5 | 1.75
| Customer meeting | Show project | Done | 0.5 | 0.5
| Group meeting | Talk about project | Done | 0.25 | 0.25
| Design | Create new design for application | Started | 5 | 2.75
| F20 | Implement functionality on client side to remove user account | Started | 6 | 2
|  |  | Sum | 21.5 | 20
|  |  | Time since previous iteration | 118.75 | 124
|  |  | Time total in the project | 140.25 | 144
8 | Requirement | Task | Status | Estimate | Actual
| Time report | Update time report for iteration 7 | Done | 0.5 | 0.25
| F20 | Familiarize self with code, download/install repo, update files | Done | 10 | 15.5
| Slack | Chat about project | Done | 0.5 | 0.25
| F20 | Update files | Done | 1 | 1.75
| Design | Add RedRiver logo as favicon | Done | 1 | 1.75
| Design | Change font | Done | 0.5 | 1.25
| Design | Add logo to application (upper left) | Done | 1 | 1.5
| Design | Implement design changes in app, including font sizes | Done | 2 | 4
| F20 | Fix before uploading to GitHub | Done | 0.5 | 0.25
| Design | Create branch, upload to repo, merge | Done | 1 | 1
|  |  | Sum | 18 | 27.5
|  |  | Time since previous iteration | 140.25 | 144
|  |  | Time total in the project | 158.25 | 171.5
9 | Requirement | Task | Status | Estimate | Actual
| Time report | Update time report for iteration 8 | Done | 1 | 1
| Peer review | Construction phase, review other group's material | Started | 2 | 1
| Group meeting | Discuss project | Done | 0.5 | 0.5
| Tutor meeting | Discuss project | Done | 0.25 | 0.25
| Group meeting | Discuss project (after tutor meeting) | Done | 0.25 | 0.25
| Time report | Update time report for iteration 9 | Done | 1 | 0.5
| Peer review | Read through group Meridium's construction material and write peer review | Done | 2 | 2.5
| Documentation | Add page "UI and design" to Wiki | Done | 1 | 1
| Coding | Work on requirement F20 | Done | 5 | 6
| Documentation | Export design image | Done | 0.25 | 0.5
|  |  | Sum | 13.25 | 13.5
|  |  | Time since previous iteration | 158.25 | 171.5
|  |  | Time total in the project | 171.5 | 185

## Sofia Ind
Iteration | Requirement | Task | Status | Estimate | Actual
0 | Lecture | Watch introduction | Done | 1.75 | 1
| Group meeting | Distribute tasks, decide on roles | Done | 1 | 0.5
| Post mortem | Read at least one post mortem from previous years, write down comments | Done | 2 | 1.5
| Github wiki | Create all wiki pages for the documentation | Done | 2 | 2
| Project plan | Start writing | Started | 1 | 1.5
| Vision | Start writing | Started | 0.5 | 0.5
| Risk list | List and prioritize as many risks as possible, write description for the document | Done | 1 | 1
| Time report | Write for the first week | Done | 1 | 0.75
| Iteration plan | Create for iteration 1 | Done | 2 | 0.75
|  |  | Sum | 12.25 | 9.5
Time since previous iteration
|  |  | Time total in the project |  | 9.5
1 | Requirement | Task | Status | Estimate | Actual
| Tutor meeting | Present the work done during start-up week | Done | 1 | 0.5
| Group meeting | Discuss iteration plan | Done | 0.5 | 0.75
| Github wiki | Renamed wikipages | Done | 0.25 | 0.25
| Customer meeting | Meeting concerning tech implementation | Done | 1 | 0.75
| BankID | Look up and send info to customer | Done | 2 | 2
| Product backlog | Read requirements | Done | 1 | 0.5
| Vision | Read the updated vision | Done | 0.25 | 0.25
| Project managing | Write list to make it clear what needs to be done before next group meeting | Done | 1 | 1
| Version control | Read instructions on README | Done | 0.25 | 0.25
| Project plan | Update | Done | 3 | 2
| Version control | Try out the version control work flow | Done | 0.5 | 0.5
| Group discussion | Discuss questions to ask the customer | Done | 0.5 | 0.5
| Product backlog | Prioritize requirements and write down questions | Done | 2 | 2
| Customer questions | Write down questions from going through the requirements | Done | 1 | 1
| Technology | Find and write down suggestion on technology to be used, discuss in Slack | Done | 1 | 1
| Product backlog | See if requirements are testable | Started | 2 | 0.25
| Test specification | Start writing tests for the high priority requirements | Not started | 4 | 0
| Time report | Write for iteration 1 | Started | 1 | 0.5
| Iteration plan | Create for iteration 2 | Started | 1 | 0.25
|  |  | Sum | 23.25 | 14.25
|  |  | Time since previous iteration |  | 9.5
|  |  | Time total in the project |  | 23.75
2 | Requirement | Task | Status | Estimate | Actual
| Time report | Write for iteration 1 | Done | 0.5 | 1
| Time report | Check the times again for iteration 1, it doesn't add up | Done | 0.5 | 0.5
| Iteration plan | Create for iteration 2 | Done | 0.75 | 2
| Tutor meeting | Present the work done during iteration 1 | Done | 1 | 0.5
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 1 | 0.5
| Group meeting | See how everyone is doing, quick update | Done | 0.5 | 0.5
| Project managing | Write list to make it clear what needs to be done before the end of the week | Done | 0.5 | 0.5
| Project managing | Document and share what the group meeting resulted in | Done | 0.5 | 0.5
| Product backlog | See if requirements are testable, comment example testcases | Done | 1.75 | 4
| Product backlog | Write explanatory test | Done | 0.5 | 0.25
| Product backlog | Sort the requirements based on priority and transfer to wiki | Done | 2 | 5.5
| Customer | Read customers answers to the question document | Done | 0.5 | 0.5
| Technology | Find and write down suggestion on technology to be used, discuss in Slack | Started | 3 | 1
| Technical documentation | Write explanatory text and list the technology etc | Done | 2 | 1
| Test specification | Start writing explanatory text | Done | 2 | 2
| Test specification | Write tests for the high priority requirements | Started | 4 | 0.25
| Test report | Start writing explanatory text | Done | 2 | 2
| Testing | Check out test frameworks to use for auto tests on React and ASP.NET | Started | 2 | 0.75
| Peer review | Update, gather and send inception material to Group 0 | Done | 4 | 3
| Time report | Write for the iteration 2 | Started | 1 | 0.75
| Iteration plan | Write analysis for iteration 2 | Not started | 0.5 | 0
|  |  | Sum | 30.5 | 27
|  |  | Time since previous iteration |  | 23.75
|  |  | Time total in the project |  | 50.75
3 | Requirement | Task | Status | Estimate | Actual
| Iteration plan | Write analysis for iteration 2 | Done | 0.5 | 0.5
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 1 | 0.75
| Tutor meeting | Present the work done during iteration 2 | Done | 1 | 0.75
| Group meeting | Discuss tutor meeting and upcoming customer meeting | Done | 0.25 | 0.25
| Customer meeting | Meeting with the customer | Done | 1 | 0.5
| Group meeting | Discuss customer meeting | Done | 0.25 | 0.25
| Peer review | Make a peer review of Group 2 inception material | Done | 3 | 3
| Peer review | Share and discuss questions asked by Group 0 on our own inception material | Done | 0.5 | 0.5
| Signal POC | Create proof of concept for Signal Encryption | Abandoned | 4 | 0.75
| Product backlog | Sort requirements based on the application being like Google Hangouts | Done | 3 | 2
| F1, F2, F3, F4 | Prototype: Design/visualize the requirements | Done | 6 | 6.5
| Testing | Check out test frameworks to use for auto tests on React and ASP.NET | Started | 1.25 | 0
| F1, F2, F3, F4 | Test specification: Write tests for the high priority requirements | Done | 4 | 2.5
| Group discussion | Discussion on Slack | Started | 2 | 1
| Peer review | Read Group 0 feedback on our own inception material | Done | 0.5 | 0.5
| Inception presentation | Start creating the presentation | Started | 3 | 2.5
| Time report | Write for iteration 3 | Done | 1 | 1
|  |  | Sum | 33.25 | 23.25
|  |  | Time since previous iteration |  | 50.75
|  |  | Time total in the project |  | 74
4 | Requirement | Task | Status | Estimate | Actual
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.75 | 0.75
| Tutor meeting | Present the work done during iteration 3 | Done | 0.75 | 0.5
| Group meeting | Discuss tutor meeting and upcoming customer meeting | Done | 0.25 | 0.5
| Customer meeting | Meeting with the customer | Done | 0.75 | 0.5
| Group meeting | Discuss customer meeting | Done | 0.25 | 0.25
| Group discussion | Discussion on Slack | Started | 1.5 | 1.5
| Project plan | Update according to Group 0 peer review | Done | 1 | 1
| Test specification | Update according to Group 0 peer review | Done | 1 | 1
| Product backlog | Update according to Group 0 peer review | Done | 1 | 1
| Vision | Update according to Group 0 peer review | Done | 2 | 2
| F2 | Prototype: Update F2 user page after login | Done | 1 | 1
| Vision | Update according to new customer information | Done | 1 | 1
| Project plan | Update according to new customer information | Done | 0.5 | 0.5
| Testing | Check out test frameworks to use for auto tests on React | Done | 1.25 | 1.25
| Testing | Set up Jest test environment for front-end | Done | 3 | 3.5
| F1, F2, F3, F4 | Create Jest tests for front-end | Started | 12 | 7 (thus far)
| Testing | Update repo with screenshot from automated jest tests and clickable html-file | Done | 0.25 | 0.25
| Test report | Update with screenshot and instructions on the automated jest tests | Done | 0.5 | 0.5
| Test specification | Update the automated test section | Done | 0.5 | 0.5
| Inception presentation | Finish the slide presentation | Done | 0.5 | 0.5
| Inception presentation | Hold our own and watch others presentation | Done | 1 | 1
| Time report | Write for iteration 4 | Done | 1 | 0.75
|  |  | Sum | 31.75 | 26.75
|  |  | Time since previous iteration |  | 74
|  |  | Time total in the project |  | 100.75
5 | Requirement | Task | Status | Estimate | Actual
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.75 | 1
| Tutor meeting | Present the work done during iteration 4 | Done | 0.75 | 0.25
| Group meeting | Discuss tutor meeting and upcoming customer meeting | Done | 0.25 | 0.25
| Group discussion | Discussion on Slack | Started | 1.5 | 1.5
| F1, F2, F3, F4 | Create Jest tests for front-end | Done | 15 | 17.5
| F1 | Add placeholders and helptext for front-end Register.js | Done | 0.5 | 0.5
| Testing | Update repo with screenshot from automated jest tests and clickable html-file | Done | 0.25 | 0.25
| Test report | Update with screenshot and instructions on the automated jest tests | Done | 0.25 | 0.25
| F1, F2, F3, F4 | Carry out the manual test cases | Done | 5 | 3
| Test report | Write report for the manual test cases | Done | 2 | 1
| Issues | Create issues for the bugs found during testing | Done | 0.75 | 0.5
| Documentation | Update documentation based on Tobias feedback from inception phase | Done | 1.5 | 1.5
| Server | Familiarize yourself with the server code to be able to work on back-end | Not started | 5 | 0
| Time report | Write for iteration 5 | Done | 1 | 0.75
|  |  | Sum | 34.5 | 28.25
|  |  | Time since previous iteration |  | 100.75
|  |  | Time total in the project |  | 129
6 | Requirement | Task | Status | Estimate | Actual
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.75 | 0.5
| Group discussion | Discussion on Slack | Started | 1.5 | 1
| Peer review | Make a peer review of Group 2 elaboration material | Done | 3 | 2.25
| Test documentation | Divide the bigger documents into smaller ones | Done | 1 | 1
| Presentation | Update presentation with information about our testing | Done | 1 | 1
| Elaboration presentation | Hold our own and watch others presentation | Done | 1 | 1
| Elaboration feedback | Read Group 0 feedback on elaboration material | Done | 0.5 | 0.5
| F1, F2, F3, F4 | Rerun the manual test cases after bugfix | Done | 3 | 1.5
| F5, F6 | Create manual test cases | Not started | 2 | 0
| F5, F6 | Carry out the manual test cases | Not started | 1.5 | 0
| Test report | Write report for the manual test cases | Not started | 2 | 0
| Issues | Create issues for the bugs found during testing | Not started | 0.75 | 0
| Development environment | Install Visual Studio for Mac to be able to work on back-end, set up mySQL client | Done | 2 | 3
| Server | Familiarize yourself with the server code to be able to work on back-end | Done | 3 | 3
| User avatar backend | Implement upload for avatar/images on back-end | Done | 5 | 5
| User avatar frontend | Implement upload for avatar/images on front-end | Done | 5 | 4
| Issues | Fix SignalR and deployment issues | Done | 2 | 1
| Issues | Create issues for the bugs connected to the image upload | Done | 0.5 | 0.5
| Time report | Write for iteration 6 | Done | 1 | 0.5
|  |  | Sum | 36.5 | 25.75
|  |  | Time since previous iteration |  | 129
|  |  | Time total in the project |  | 154.75
7 | Requirement | Task | Status | Estimate | Actual
| Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.75 | 0.5
| Tutor meeting | Present the work done during iteration 6 | Done | 0.5 | 0.25
| Group meeting | Discuss tutor meeting and upcoming customer meeting | Done | 0.25 | 0.25
| Group discussion | Discussion on Slack | Done | 1.5 | 1
| F5, F6, F7, F47 | Create manual test cases | Done | 2.5 | 2
| F5, F6, F7, F47 | Carry out the manual test cases | Done | 1.5 | 1.5
| Test report | Write report for the manual test cases | Done | 2 | 1.5
| Issues | Create issues for the bugs found during testing | Done | 0.75 | 0.75
| F13 | Implement on back-end | Started | 6 | 8.75
| Customer meeting | Meeting with the customer | Done | 0.5 | 0.5
| Time report | Write for iteration 7 | Done | 1 | 0.5
|  |  | Sum | 17.25 | 17.5
|  |  | Time since previous iteration |  | 154.75
|  |  | Time total in the project |  | 172.25
8 | Requirement | Task | Status | Estimate | Actual
| Tutor meeting | Present the work done during iteration 7 | Done | 0.5 | 0.5
| Group meeting | Discuss tutor meeting, the new iteration and distribute tasks | Done | 0.25 | 0.25
| Group discussion | Discussion on Slack | Started | 1.5 | 1.25
| F10, F13, F20 | Create manual test cases | Done | 2.5 | 2
| U3, U4, U5 | Create manual test cases | Done | 1 | 1
| F13 | Implement on back-end | Done | 4 | 9
| F13 | Work on the known issues | Done | 4 | 5.75
| Construction phase | Update documentation so that it answers the questions in the peer review | Done | 3 | 2.75
| Time report | Write for iteration 8 | Done | 1 | 0.5
|  |  | Sum | 17.75 | 23
|  |  | Time since previous iteration |  | 172.25
|  |  | Time total in the project |  | 195.25
9 | Requirement | Task | Status | Estimate | Actual
| Group meeting | Discuss the new iteration and distribute tasks | Done | 0.5 | 0.5
| Tutor meeting | Present the work done during iteration 8 | Done | 0.5 | 0.25
| Group meeting | Discuss tutor meeting | Done | 0.25 | 0.25
| Group discussion | Discussion on Slack | Started | 1.5 | 1
| F5, F6, F7, F47 | Regression test: Carry out the manual test cases | Done | 1.5 | 1
| F10, F13, F20, U3, U4, U5 | Carry out the manual test cases | Not started | 3
| Test report | Write report for the manual test cases | Started | 2 | 1
| Issues | Create issues for the bugs found during testing | Started | 0.75 | 0.5
| Handover | SendGrid documentation for the customer | Done | 2 | 2.75
| Construction feedback | Give feedback to group 2 material and send to Frida | Done | 2 | 2.25
| F13 | Solve problem with emails not being sent to live.se | Done | 1 | 1
| Time report | Write for iteration 9 | Done | 1 | 0.5
|  |  | Sum | 15.5 | 11
|  |  | Time since previous iteration |  | 195.25
|  |  | Time total in the project |  | 206.25
10 | Requirement | Task | Status | Estimate | Actual
| Construction feedback | Read Group 0 feedback on construction material | Done | 0.25 | 0.25
| Test report | Update based on construction feedback | Done | 0.25 | 0.25
| Group meeting | Discuss the new iteration and distribute tasks | Done | 0.5 | 0.25
| Group discussion | Discussion on Slack | Started | 1.5 | 1.25
| End presentation | Hold our own and watch others presentation | Done | 1.5 | 1.5
| F10, F13, F20, U3, U4, U5 | Carry out the manual test cases | Done | 3 | 3
| Test report | Write report for the manual test cases | Done | 2 | 1.5
| Issues | Create issues for the bugs found during testing | Done | 0.5 | 0.5
| Final report | Create and write the final report | Started | 4 | 8.5
| Stress test | Ran through Andrews jMeter stress tests | Done | 0.25 | 0.25
| Stress test | Update test report with result from jMeter tests | Done | 0.5 | 0.5
| Demo video | Record demo for video calls (Didn't work for some reason) | Done | 0.5 | 0.75
| Regression testing | Test all implemented requirements to find all potential bugs (write test report + create issues) | Done | 8 | 7
| Customer meeting | Handover of the project | Done | 1 | 0.5
| Time report | Write for iteration 10 | Started | 1 | 0.75
|  |  | Sum | 23.75 | 26.75
|  |  | Time since previous iteration |  | 206.25
|  |  | Time total in the project |  | 233

## Iteration 5 Summary
Category | Member | Requirement | Task | Status | Time(h)
Architecture | Andrew | Azure setup | Fix deploy to Azure | Done | 1
Architecture | Jimmy | Azure setup | Fix Azure problems. Setup new Azure webapps and automatic deployment from Github. | Done | 2
Coding | Sofia | F1 | Add placeholders and helptext for front-end Register.js | Done | 0.5
Coding | Jimmy | F1-F4 | Client: Fix bugs and refactor. Also add layouts for screen breakpoints. | Done | 9.75
Coding | Jimmy | F5 User chat room | Start implement on client. Continue next iteration. | Done | 3.75
Coding | Andrew | F5/F6 | Write server code for group chat | Done | 13 | Category | Time
Coding | Sofia | Issues | Create issues for the bugs found during testing | Done | 0.5 | Architecture | 3
Customer meeting | Andrew | Customer meeting | Delivery | Done | 0.5 | Coding | 27.5
Customer meeting | Jimmy | Customer meeting | Meeting with the customer | Done | 0.25 | Customer meeting | 1.25
Customer meeting | Linda | Customer meeting | Start Google Hangouts video call for customer meeting, send link to customer | Done | 0.25 | Documentation | 21
Customer meeting | Linda | Customer meeting | Discuss and show application | Done | 0.25 | Group communication | 6.25
Documentation | Andrew | Documentation | Update elaboration documentation | Done | 1 | Group meeting | 2.25
Documentation | Jimmy | Documentation | Explain WebRTC and create diagrams. | Done | 2.5 | Knowledge | 0
Documentation | Linda | Documentation | Summarize individual time reports for iteration 4 | Done | 4.5 | Testing | 24.5
Documentation | Linda | Documentation | Write analysis of iteration 4, add to page for iteration 5 | Done | 0.5 | Tutor Meeing | 1.5
Documentation | Sofia | Documentation | Update documentation based on Tobias feedback from inception phase | Done | 1.5
Documentation | Linda | Peer review | Go through Elaboration questions for peer review, write bullet list of things to fix | Done | 0.25
Documentation | Linda | Peer review | Prepare documentation for sending Elaboration material to group 0 | Done | 1
Documentation | Linda | Peer review | Clone down Wiki and repository | Done | 0.25
Documentation | Linda | Peer review | Send Wiki and repository to group 0 | Done | 0.25
Documentation | Andrew | Time report | Write for iteration 5 | Done | 0.5
Documentation | Andrew | Time report | Write for iteration 6 | Started | 0.5
Documentation | Jimmy | Time report | Write for this week | Done | 0.5
Documentation | Linda | Time report | Plan iteration 5 | Done | 0.5
Documentation | Linda | Time report | Write iteration plan for iteration 5 | Done | 0.5
Documentation | Linda | Time report | Update my own time report for iteration 4 | Done | 0.75
Documentation | Linda | Time report | Add my own time report for iteration 5 | Done | 0.25
Documentation | Linda | Time report | Write time report for entire group for iteration 4 | Done | 4.5
Documentation | Linda | Time report | Update my own time report for iteration 5 | Done | 0.5
Documentation | Sofia | Time report | Write for iteration 5 | Done | 0.75
Group communication | Jimmy | Group communication | Discussion on slack | Done | 0.75
Group communication | Linda | Group communication | Weekly group meeting on Slack | Done | 1
Group communication | Linda | Group communication | Discuss project | Done | 0.25
Group communication | Linda | Group communication | Read messages on Slack | Done | 0.75
Group communication | Linda | Group communication | Chat on Slack about upcoming customer meeting | Done | 1
Group communication | Linda | Group communication | Group meeting, discuss customer meeting and what to do next | Done | 0.5
Group communication | Linda | Group communication | Chat about project, find emulators for device testing, found blisk.io | Done | 0.5
Group communication | Sofia | Group communication | Discussion on Slack | Started | 1.5
Group meeting | Andrew | Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5
Group meeting | Jimmy | Group meeting | Discuss customer meeting | Done | 0.5
Group meeting | Sofia | Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 1
Group meeting | Sofia | Group meeting | Discuss tutor meeting and upcoming customer meeting | Done | 0.25
Knowledge | Linda | Project knowledge | Refresh knowledge on React and JavaScript | Not Started | 0
Knowledge | Sofia | Server | Familiarize yourself with the server code to be able to work on back-end | Not started | 0
Testing | Sofia | F1, F2, F3, F4 | Create Jest tests for front-end | Done | 17.5
Testing | Sofia | F1, F2, F3, F4 | Carry out the manual test cases | Done | 3
Testing | Sofia | Test report | Update with screenshot and instructions on the automated jest tests | Done | 0.25
Testing | Sofia | Test report | Write report for the manual test cases | Done | 1
Testing | Andrew | Testing | Initiate xUnit testing framework | Done | 2
Testing | Linda | Testing | Test application in browserstack | Done | 0.5
Testing | Sofia | Testing | Update repo with screenshot from automated jest tests and clickable html-file | Done | 0.25
Tutor meeting | Andrew | Tutor meeting | Present the work done during iteration 4 | Done | 1
Tutor meeting | Linda | Tutor meeting | Go through iteration plan for week, check time report, discuss risks, talk about possible problems | Done | 0.25
Tutor meeting | Sofia | Tutor meeting | Present the work done during iteration 4 | Done | 0.25
|  |  |  | Sum | 87.25

## Iteration 6 Summary
Category | Member | Requirement | Task | Status | Time(h)
Architecture | Jimmy | Azure Setup | Fix issue with auto-deployment to Azure. Changed Azure-plan from free to basic. | Done | 0.75
Coding | Andrew | F1 | Improving aspects of F1, take care of existing issues | Done | 6
Coding | Jimmy | F5 User chat room | Implement on client. Continue next iteration | Done | 7
Coding | Andrew | F5/F6 | Refactor/improve/test server code for group chat | Started | 6
Coding | Jimmy | F6 User text message | Implement on client. Continue next iteration | Done | 4
Coding | Sofia | Issues | Create issues for the bugs found during testing | Not started | 0 | Category | Time
Coding | Sofia | Issues | Fix SignalR and deployment issues | Done | 1 | Architecture | 0.75
Coding | Sofia | Issues | Create issues for the bugs connected to the image upload | Done | 0.5 | Coding | 39.5
Coding | Sofia | User avatar backend | Implement upload for avatar/images on back-end | Done | 5 | Customer meeting | 0
Coding | Jimmy | User Avatar bugs | Fix bugs for image upload | Done | 5.25 | Documentation | 35.25
Coding | Sofia | User avatar frontend | Implement upload for avatar/images on front-end | Done | 4 | Group communication | 1.75
Documentation | Sofia | Elaboration feedback | Read Group 0 feedback on elaboration material | Done | 0.5 | Group meeting | 1.5
Documentation | Andrew | Elaboration presentation | Prepare elaboration presentation | Done | 2 | Knowledge | 6
Documentation | Jimmy | Elaboration Presentation | Attend presentation of Elaboration by all groups | Done | 1 | Testing | 2.5
Documentation | Linda | Elaboration Presentation | Write presentation for Elaboration | Done | 6.75 | Tutor Meeing | 0
Documentation | Linda | Elaboration Presentation | Find our peer review for presentation | Done | 0.25
Documentation | Linda | Elaboration Presentation | Write bullet list of our peer review for presentation | Done | 1.25
Documentation | Linda | Elaboration Presentation | Time presentation for Elaboration | Done | 0.25
Documentation | Linda | Elaboration Presentation | Transfer presentation manuscript to paper | Done | 2
Documentation | Linda | Elaboration Presentation | Hold presentation and peer review, listen to other groups | Done | 1
Documentation | Sofia | Elaboration Presentation | Hold our own and watch others presentation | Done | 1
Documentation | Sofia | Elaboration Presentation | Update presentation with information about our testing | Done | 1
Documentation | Andrew | Group documentation | Move time reports, milestones | Done | 2
Documentation | Andrew | Peer review | Read other group's elaboration and comment | Done | 3
Documentation | Jimmy | Peer Review | Review Meridium-group elaboration | Done | 0.5
Documentation | Linda | Peer review | Read through group Meridium's Elaboration material | Done | 1
Documentation | Linda | Peer review | Read through peer review from other group | Done | 0.5
Documentation | Sofia | Peer review | Make a peer review of Group 2 elaboration material | Done | 2.25
Documentation | Jimmy | Server Architecture | Update Diagrams | Done | 6
Documentation | Andrew | Time report | Write for iteration 6 | Done | 0.5
Documentation | Andrew | Time report | Write for iteration 7 | Started | 0.5
Documentation | Jimmy | Time report | Write for this week | Done | 0.5
Documentation | Linda | Time report | Update my own time report for iteration 5 | Done | 1
Documentation | Sofia | Time report | Write for iteration 6 | Done | 0.5
Group communication | Jimmy | Group discussion | Discussion on slack | Done | 0.75
Group communication | Sofia | Group discussion | Discussion on Slack | Started | 1
Group meeting | Andrew | Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5
Group meeting | Jimmy | Group meeting | Discuss latest iteration. Distribute tasks for next. | Done | 0.5
Group meeting | Sofia | Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5
Knowledge | Sofia | Development environment | Install Visual Studio for Mac to be able to work on back-end, set up mySQL client | Done | 3
Knowledge | Sofia | Server | Familiarize yourself with the server code to be able to work on back-end | Done | 3
Testing | Sofia | F1, F2, F3, F4 | Rerun the manual test cases after bugfix | Done | 1.5
Testing | Sofia | F5, F6 | Create manual test cases | Not started | 0
Testing | Sofia | F5, F6 | Carry out the manual test cases | Not started | 0
Testing | Andrew | Server Testing | Elaborate xUnit testing framework | Not started | 0
Testing | Sofia | Test documentation | Divide the bigger documents into smaller ones | Done | 1
Testing | Sofia | Test report | Write report for the manual test cases | Not started | 0
Testing | Linda | WCAG 2.1 | Write bullet list of WCAG 2.1 | Started | 1
|  |  |  | Sum | 87.5

## Iteration 7 Summary
Category | Member | Requirement | Task | Status | Time(h)
Accessibility | Andrew | U2 | Create WCAG spreadsheet, read docs | Started | 5
Accessibility | Linda | WCAG 2.1 | Write bullet list of WCAG 2.1 | Done | 8.75
Accessibility | Linda | WCAG 2.1 | Work on bullet list, send link to group | Done | 0.25
Coding | Jimmy | F1-F10 Bug Fix | Fix discovered bugs and update css. Continue next iteration. | Done | 3
Coding | Jimmy | F10 Video Call | Implement Video call. | Done | 12.25
Coding | Sofia | F13 | Implement on back-end | Started | 8.75 | Category | Time
Coding | Linda | F20 | Implement functionality on client side to remove user account | Started | 2 | Accessibility | 14
Coding | Jimmy | F5 User chat room | Implement on client. | Done | 5 | Architecture | 0
Coding | Andrew | F5/F6 | Refactor/improve/test server code for group chat | Started | 6 | Coding | 49
Coding | Jimmy | F6-F7 User text message | Implement on client. | Done | 6 | Customer meeting | 2.5
Coding | Linda | Implementation | Clone repository, set up development environment | Done | 1 | Design | 2.75
Coding | Andrew | Issues | Take care of existing issues | Done | 5 | Documentation | 6.75
Customer meeting | Andrew | Customer Meeting | Delivery | Done | 1 | Group communication | 2
Customer meeting | Jimmy | Customer meeting | Meeting with the customer | Done | 0.5 | Group meeting | 3.25
Customer meeting | Linda | Customer meeting | Show project | Done | 0.5 | Knowledge | 0.75
Customer meeting | Sofia | Customer meeting | Meeting with the customer | Done | 0.5 | Testing | 5.75
Design | Linda | Design | Create new design for application | Started | 2.75 | Tutor Meeting | 0.75
Documentation | Andrew | Group documentation | Time reports, milestones, iteration summary | Done | 2 |  | 87.5
Documentation | Andrew | Time report | Write for iteration 7 | Done | 0.5
Documentation | Andrew | Time report | Write for iteration 8 | Started | 0.5
Documentation | Jimmy | Time report | Write for this week | Done | 0.5
Documentation | Linda | Time report | Update my own time report for iteration 6 | Done | 1
Documentation | Linda | Time report | Update my own time report for iteration 7 | Done | 1.75
Documentation | Sofia | Time report | Write for iteration 7 | Done | 0.5
Group communication | Jimmy | Group discussion | Discussion on slack | Done | 1
Group communication | Sofia | Group discussion | Discussion on Slack | Done | 1
Group meeting | Andrew | Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5
Group meeting | Jimmy | Group meeting | Discuss tutor meeting | Done | 0.25
Group meeting | Jimmy | Group meeting | Discuss latest iteration. Distribute tasks for next. | Done | 0.5
Group meeting | Jimmy | Group meeting | Discuss customer meeting | Done | 0.25
Group meeting | Linda | Group meeting | Talk about project, divide tasks | Done | 0.5
Group meeting | Linda | Group meeting | Talk about project, divide tasks | Done | 0.25
Group meeting | Linda | Group meeting | Talk about project | Done | 0.25
Group meeting | Sofia | Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5
Group meeting | Sofia | Group meeting | Discuss tutor meeting and upcoming customer meeting | Done | 0.25
Knowledge | Linda | Implementation | Build and run application, familiarize self with code in App.js | Done | 0.75
Testing | Sofia | F5, F6, F7, F47 | Create manual test cases | Done | 2
Testing | Sofia | F5, F6, F7, F47 | Carry out the manual test cases | Done | 1.5
Testing | Sofia | Issues | Create issues for the bugs found during testing | Done | 0.75
Testing | Sofia | Test report | Write report for the manual test cases | Done | 1.5
Tutor Meeting | Jimmy | Tutor meeting | Present the work done | Done | 0.25
Tutor Meeting | Linda | Tutor meeting | Talk about project, reports and presentation | Done | 0.25
Tutor Meeting | Sofia | Tutor meeting | Present the work done during iteration 4 | Done | 0.25
|  |  |  | Sum | 87.5

## Iteration 8 Summary
Category | Member | Requirement | Task | Status | Time(h)
Coding | Andrew | F5-F6 | Server: Update user details, password | Done | 8
Coding | Jimmy | F5-F6 | Client: Update user details, password | Done | 3
Coding | Jimmy | F1-F13 | Fix discovered bugs and update css. | Done | 16
Coding | Sofia | F13 | Work on the known issues | Done | 5.75
Coding | Sofia | F13 | Implement on back-end | Done | 9
Coding | Linda | F20 | Familiarize self with code, download/install repo, update files | Done | 15.5 | Category | Time
Coding | Linda | F20 | Fix before uploading to GitHub | Done | 0.25 | Coding | 59.25
Coding | Linda | F20 | Update files | Done | 1.75 | Design | 9.5
Design | Linda | Design | Add RedRiver logo as favicon | Done | 1.75 | Documentation | 14.25
Design | Linda | Design | Change font | Done | 1.25 | Group communication | 3
Design | Linda | Design | Add logo to application (upper left) | Done | 1.5 | Group meeting | 1
Design | Linda | Design | Implement design changes in app, including font sizes | Done | 4 | Testing | 7
Design | Linda | Design | Create branch, upload to repo, merge | Done | 1 | Tutor Meeting | 1.5
Documentation | Andrew | Group documentation | Move time reports, milestones | Done | 2 |  | 95.5
Documentation | Andrew | Time report | Write for iteration 8 | Done | 0.5
Documentation | Jimmy | Time report | Write for iteration 8 | Done | 0.25
Documentation | Linda | Time report | Update time report for iteration 8 | Done | 0.25
Documentation | Sofia | Time report | Write for iteration 8 | Done | 0.5
Documentation | Andrew | Handin | Update documentation ahead of handin | Done | 4
Documentation | Sofia | Construction phase | Update documentation so that it answers the questions in the peer review | Done | 2.75
Documentation | Jimmy | Construction phase | Update technical documentation, diagrams and clients README.md | Done | 4
Group communication | Jimmy | Group discussion | Discussion on slack | Done | 1.5
Group communication | Sofia | Group discussion | Discussion on Slack | Done | 1.25
Group communication | Linda | Group discussion | Chat about project in Slack | Done | 0.25
Group meeting | Andrew | Group meeting | Discuss work done, the new iteration plan and distribute tasks | Done | 0.5
Group meeting | Jimmy | Group meeting | Discuss tutor meeting | Done | 0.25
Group meeting | Sofia | Group meeting | Discuss tutor meeting, the new iteration and distribute tasks | Done | 0.25
Testing | Andrew | F1-F6 | Write tests for adding, deleting, user details etc. | Started | 4
Testing | Sofia | F10, F13, F20 | Create manual test cases | Done | 2
Testing | Sofia | U3, U4, U5 | Create manual test cases | Done | 1
Tutor Meeting | Jimmy | Tutor meeting | Present the work done | Done | 0.5
Tutor Meeting | Sofia | Tutor meeting | Present the work done during iteration 7 | Done | 0.5
Tutor Meeting | Andrew | Tutor meeting | Tutor Meeting | Done | 0.5
|  |  |  | Sum | 95.5

## Iteration 9 Summary
Category | Member | Requirement | Task | Status | Time(h)
Coding | Jimmy | F1-F13 | Fix discovered bugs and update css. | Done | 6.5
Coding | Sofia | F13 | Solve problem with emails not being sent to live.se | Done | 1
Coding | Linda | F20 | Work on requirement F20 | Done | 6
Documentation | Andrew | Construction feedback | Give other group construction feedback | Done | 3
Documentation | Linda | Construction feedback | Construction phase, review other group's material | Done | 1 | Category | Time
Documentation | Linda | Construction feedback | Read through group Meridium's construction material and write peer review | Done | 2.5 | Coding | 13.5
Documentation | Sofia | Construction feedback | Give feedback to group 2 material and send to Frida | Done | 2.25 | Documentation | 21.25
Documentation | Andrew | Final presentation | Writing presentation for product | Done | 3 | Group communication | 1.75
Documentation | Jimmy | Group documentation | Move time reports. Analysis of Iteration 8 | Done | 2 | Group meeting | 2.25
Documentation | Sofia | Handover | SendGrid documentation for the customer | Done | 2.75 | Testing | 7.5
Documentation | Andrew | Time report | Write for iteration 9 | Done | 0.5 | Tutor Meeting | 1.25
Documentation | Andrew | Time report | Write for iteration 10 | Done | 0.5 |  | 47.5
Documentation | Jimmy | Time report | Write for iteration 9 | Done | 0.25
Documentation | Linda | Time report | Update time report for iteration 8 | Done | 1
Documentation | Linda | Time report | Update time report for iteration 9 | Done | 0.5
Documentation | Sofia | Time report | Write for iteration 9 | Done | 0.5
Documentation | Linda | Wiki | Export design image | Done | 0.5
Documentation | Linda | Wiki | Add page "UI and design" to Wiki | Done | 1
Group communication | Jimmy | Group discussion | Discussion on slack | Done | 0.75
Group communication | Sofia | Group discussion | Discussion on Slack | Done | 1
Group meeting | Jimmy | Group meeting | Discuss latest iteration. Distribute tasks for next. | Done | 0.5
Group meeting | Linda | Group meeting | Discuss project | Done | 0.5
Group meeting | Sofia | Group meeting | Discuss the new iteration and distribute tasks | Done | 0.5
Group meeting | Jimmy | Group meeting | Discuss tutor meeting | Done | 0.25
Group meeting | Linda | Group meeting | Discuss project (after tutor meeting) | Done | 0.25
Group meeting | Sofia | Group meeting | Discuss tutor meeting | Done | 0.25
Testing | Andrew | Load testing | Server load testing | Done | 3
Testing | Andrew | SignalR | Writing tests for SignalR | Done | 2
Testing | Sofia | F5, F6, F7, F47 | Regression test: Carry out the manual test cases | Done | 1
Testing | Sofia | Test report | Write report for the manual test cases | Done | 1
Testing | Sofia | Issues | Create issues for the bugs found during testing | Done | 0.5
Tutor Meeting | Linda | Tutor meeting | Discuss project | Done | 0.25
Tutor Meeting | Jimmy | Tutor meeting | Present the work done | Done | 0.25
Tutor Meeting | Sofia | Tutor meeting | Present the work done during iteration 8 | Done | 0.25
Tutor Meeting | Andrew | Tutor meeting | Tutor Meeting | Done | 0.5
|  |  |  | Sum | 47.5