## Dashboard
Status | Functionality | Usability | Reliability | Performance | Supportability | Total
Not implemented | 35 | 0 | 3 | 0 | 1 | 39
Started | 2 | 4 | 2 | 1 | 0 | 9
Implemented | 10 | 2 | 5 | 0 | 0 | 17
Sum | 47 | 6 | 10 | 1 | 1 | 65

## Functionality
ID | Name | Description/User story | Dependencies | Status | Priority | Author | Test case | Testable (y/n) | Test case Author | Comments | Prototype
F1 | User register | A user must be able to register to the app. | - | Implemented | 5 | Linda/Sofia | T.1.1, T.1.2, T.1.3, T.1.4, T.1.5 | y | Sofia | Sofia: Testcases: 1. User register with correct information. 2. User register with username missing. 3. User register with password missing. 4. User register with existing username. 5. User register with username and password missing. | Sofia
F2 | User login | A user must be able to login to the app. | F1 | Implemented | 5 | Sofia | T.2.1, T.2.2, T.2.3, T.2.4, T.2.5,T.2.6 | y | Sofia | Sofia: Testcases: 1. User log in with correct information. 2. User log in with username missing. 3. User log in with password missing. 4. User log in with wrong username. 5. User log in with wrong password. 6. User log in with username and password missing. | Sofia
F3 | User - own data access | A user should have access to their own personal information. | F1, F2 | Implemented | 5 | Andrew | T.3.1 | y | Sofia | Sofia: Testcase: 1. Browse user information. | Sofia
F4 | Add friends | A user should be able to add friends to a friendslist. | F1, F2 | Implemented | 5 | Sofia | T.4.1, T.4.2, T.4.3, T.4.4, T.4.5 | y | Sofia | Sofia: Testcases: 1. User adds friend by username 2. User adds nonexistent user as friend by username. 3. User gets friend request from other user. 4. User approves friend request from other user. 5. User denies friend request from other user. | Sofia
F5 | User chat room | A user should be able to create chat rooms to which other users can connect. | F1, F2 | Implemented | 5 | Linda | T.5.1, T.5.2, T.5.3 | y | Sofia | Sofia: Testcases: 1. User creates chat room. 2. User adds friend to already existing chat room. 3. User leaves chat room.
F6 | User text message | A user can send text messages to other users. | F1, F2 | Implemented | 5 | Andrew | T.6.1, T.6.2 | y | Linda/Sofia | Sofia: Testcase: 1. A user sends text message to another user. 2. A user receives text message from another user.
F7 | Logs through UI | The communication log is available to the user through the app’s UI. | F1, F2 | Implemented | 5 | Andrew | T.7.1 | y | Sofia | Sofia: Testcase: 1. User checks communication/chat log.
F8 | User camera photo message | A user can take a picture with the device camera and send it to other users. | F1, F2 | Not implemented | 4 | Andrew | - | y | - | Sofia: Testcases: 1. User takes picture with device camera. 2. User sends picture to another user.
F9 | User stored image message | A user can choose an image stored on the device and send it to other users. | F1, F2 | Not implemented | 4 | Andrew | - | y | - | Sofia: Testcases: 1. User choose picture from device hard drive. 2. User sends a picture to another user.
F10 | User video call | A user can call another user and communicate with video. | F1, F2 | Implemented | 4 | Andrew | T.10.1, T.10.2, T.10.3, T.10.4, T.10.5, T.10.6 | y | Sofia | Sofia: Testcase: 1. A user makes a video call to another user. 2. A user receives a video call from another user. 3. A user can ignore a video call. 4. A user can mute/unmute their microphone. 5. A user can hide/show their camera feed. 6. A user can end the video call.
F11 | User support | The user can contact admin via the UI for support. | F1, F2 | Not implemented | 4 | Linda | - | y | - | Sofia: Testcases: 1. User creates chat with admin. (or mail for support?) 2. User sends message to admin. 3. User receives message from admin.
F12 | Admin/user chat | The admin can chat with users. | F1, F2 | Not implemented | 4 | Linda | - | y | - | Sofia: Testcases: 1. Admin creates chat with user. 2. User creates chat with admin. 3. Admin sends message to user. 4. Admin receives message from user. 5. User sends message to admin. 6. User receives message from admin.
F13 | Consent Mail | Before a user begins using the app, the user receives a mail with a link. Clicking upon the link allows the user to consent to use the app. | F1 | Implemented | 4 | Andrew | T.13.1, T.13.2, T.13.3 | y | Sofia | Sofia: Testcase: 1. User receives confirmation email. 2. User leaves consent and confirms their email. 3. User does not leave consent nor confirms their email.
F14 | User consent withdrawal | The user can at any time withdraw their consent via the app’s UI. | F1, F2 | Not implemented | 4 | Andrew | - | y | - | Sofia: Testcase: 1. User withdraw consent.
F15 | Consent withdrawal message | If consent is withdrawn, the user receives a message confirming that the user will be removed from the system and that all records of communication will be removed. | F1, F14 | Not implemented | 4 | Andrew | - | y | - | Sofia: Testcase: 1. User receives message confirming removal from system.
F16 | Consent withdrawal confirmation | When the user receives such a message, the user can confirm removal from system. | F1, F14, F15 | Not implemented | 4 | Andrew | - | y | - | Sofia: Testcase: 1. User confirms removal from system.
F17 | User removal upon consent withdrawal | If consent is withdrawn, the user is removed from the system within 24 hours. | F1, F14, F15, F16 | Not implemented | 4 | Andrew | - | y | - | Sofia: Testcase: 1. Admin removes user with withdrawn consent.
F18 | User data removal upon consent withdrawal | If consent is withdrawn, all records of communication are removed from the system. Including the chat logs of other users where the user has participated. | F1, F14, F15, F16, F17 | Not implemented | 4 | Andrew | - | y/n | - | BIG testcase where we have to manually go through all chats the user had and see that everything is removed. Testcase: 1. All user data is removed from the system.
F19 | User account inactivation | It should be possible for a user’s account to be inactivated (unclear if the user can do this or admin or both?) | F1 | Not implemented | 3 | Andrew | - | y | - | Sofia: Testcase: 1. Admin inactivates user account.
F20 | User account deletion | It should be possible for a user’s account to be terminated (unclear if user does this or admin or both) | F1 | Started | 3 | Andrew | T.20.1, T.20.2 | y | Sofia | Sofia: Testcase: 1. Admin/user deletes user account. 2. User logs in with deleted account.
F21 | Log erasure notification | The user is advised upon signup that logs will be erased after a period of time. | F1 | Not implemented | 3 | Linda | - | y | - | Sofia: Testcases: 1. User is advised about log erasure upon signup.
F22 | Log storage time | Logs should not be stored for a longer period of time than required by law. | F1 | Not implemented | 3 | Andrew | - | y | - | Sofia: Här måste vi som grupp förtydliga hur lång tid lagen säger att man får lagra loggarna. Testcase: 1. Logs erased after [insert time period from law].
F23 | Registered relative | Each user should have a registered relative | F1 | Not implemented | 2 | Linda | - | y | - | Andrew: But can a user be created without a relative? And does the relative have to be a user? And how do we know the relative is a relative.....and so on. Sofia: Testcases: 1. User have registered relative. 2. User does not have registered relative.
F24 | Registered relative can withdraw consent | The registered relative should be able to withdraw consent on behalf of the user | F1 | Not implemented | 2 | Linda | - | y | - | Sofia: Testcases: 1. User relative withdraws consent.
F25 | Registered relative can erase users account | The registered relative should be able to erase the users account | F1 | Not implemented | 2 | Linda | - | y | - | Sofia: Testcases: 1. User relative erase users account.
F26 | User channel creation | A user can create a channel and send live from her/his camera. | F1, F2 | Not implemented | 1 | Andrew | - | y | - | Jimmy: Use third party-service to reduce heavy loads on server? Sofia: Testcases: 1. User creates a channel. 2. User live streams from channel with device camera.
F27 | User channel invite | A user can invite other users to watch the channel by copying a link and distribute that link to the viewers. | F1, F2, F26 | Not implemented | 1 | Andrew | - | y | - | Sofia: Testcase: 1. User copies live stream link. 2. User distributes link to viewers (ska vi ha facebook, twitter, instagram knappar för detta?)
F46 | Approve/Deny friendship | A user should be able to approve/deny friend requests. | F4 | Started | 1 | Andrew | T.4.1, T.4.2, T.4.3, T.4.4, T.4.5 | y | Sofia | Sofia: Testcases: 1. User adds friend by username 2. User adds nonexistent user as friend by username. 3. User gets friend request from other user. 4. User approves friend request from other user. 5. User denies friend request from other user.
F47 | User profile picture | A user should be able to upload a profile picture. | F3 | Implemented | 1 | Sofia | T.47.1, T.47.2, T.47.3, T.47.4, T.47.5 | y | Sofia | Sofia: Testcases: 1. User uploads image as profile picture. 2. User uploads pdf as profile picture. 3. User uploads nonexistent file. 4. User uploads an image with width 801px. 5. User uploads an image with length 801px.
In terms of time
ID | Name | Description/User story | Dependencies | Status | Priority | Author | Test case | Testable (y/n) | Test case Author | Comments
F28 | User levels | The system should have three user levels – superuser, admin and user. | - | Not implemented | 5 | Andrew | T.28.1, T.28.2, T.28.3 | y | Linda/Sofia | Sofia: Testcases: 1. Browse superuser page. 2. Browse admin page. 3. Browse user page.
F29 | Admin UI | The system should have an admin UI. | - | Not implemented | 5 | Sofia | - | y | Linda | Sofia: Testcase: 1. Browse admin page.
F30 | Admin registration approval/denial | Registrations must be approved by an admin. | - | Not implemented | 5 | Sofia | - | y | - | Sofia: Testcases: 1. Admin approves a users access request to app. 2. Admin deny a users access request to app.
F31 | Admin UI user add | An admin should be able to add new users by using the admin UI | - | Not implemented | 4 | Andrew | - | y/n | - | Sofia: Är det endast admin som kan lägga till/registrera nya användare? Kan en användare inte registrera sig själv? Ska det inte finnas en registreringssida? If not using Mobile BankID, testcases: 1. Admin add new user to application.
F32 | Admin UI user removal | An admin should be able to remove users by using the admin UI. | - | Not implemented | 4 | Andrew | - | y/n | - | Sofia: If not using Mobile BankID, testcases: 1. Admin removes user from application.
F33 | Admin UI visibility. | The admin UI is only visible to admins. | - | Not implemented | 4 | Linda | - | y | - | Sofia: Testcases: 1. Admin sees admin area/page. 2. User does not see admin area/page. 3. Superuser does not see admin area/page.
F34 | Admin can see user information | An admin should be able to see all personal information belonging to a user. | - | Not implemented | 4 | Andrew | - | y | - | Sofia: Testcase: 1. Admin browse user personal information.
F35 | Admin can back up data | Admin should be able to easily restore all data in the system, such as user accounts | - | Not implemented | 3 | Linda | - | y/n | - | Sofia: "Easily" is subjective. Needs to be more clear what the customer means by "easily". "Easily" is subjective. Testcases: 1. Admin restores user account. 2. Admin restores chat logs. 3. Admin restores ...
F36 | Superuser can limit admin's rights | A superuser should be able to limit an admin’s rights so that the admin may only see the first 6 figures in the users social security number and the users first name. | - | Not implemented | 3 | Andrew | - | y | - | Sofia: Testcase: 1. Superuser grants admin right to see 10 digit social security number. 2. Superuser limits admin's right to see 10 digit social security number.
F37 | Limit superuser's access to personal data | The superuser can not see any personal information in the system – only allow or forbid an admin to see the last four digits in a user’s social security number and other personal information. | - | Not implemented | 3 | Andrew | - | y | - | Sofia: Testcase: 1. Browse superuser page.
F38 | Data access | Access to user data should be limited to the user and admin (to the degree decided by a superuser) | - | Not implemented | 3 | Andrew | - | n | - | Jimmy: Presumably, when a superuser turns off an admin's ability to see a user's personal info, this applies to all users - or is it done on a per user basis? Sofia: Not clear who "those who need such access" are.
F39 | Logs | All communication should be securely stored in logs. | - | Not implemented | 2 | Andrew | - | y/n | - | Sofia: Securely has to be more specific. Testcase: 1. Communication stores in logs.
F40 | Data gathering | Only necessary user data should be gathered. | - | Not implemented | 2 | Andrew | - | n | - | Sofia: Vad är necessary user data? Detta måste kunden förtydliga.
F41 | Admin UI temporary password set | An admin should be able to set a temporary password for users by using the admin UI. | - | Not implemented | 1 | Andrew | - | y/n | - | Jimmy and Sofia: Unnecessary if using Mobilt BankID? Sofia: If not using Mobile BankID, testcase: 1. Admin set temporary password for new user.
F42 | Admin UI temporary password mail | When a temporary password is set the user should receive notification via mail. | - | Not implemented | 1 | Andrew | - | y/n | - | Jimmy and Sofia: Unnecessary if using Mobilt BankID? Sofia: If not using Mobile BankID, testcase: 1. User receive mail about temporary password.
F43 | User changes password after mail | The user, upon receiving email notification of a temporary password, should be able to log in and change password. | - | Not implemented | 1 | Andrew | - | y/n | - | Jimmy: Unnecessary if using Mobilt BankID? Sofia: If not using Mobile BankID, testcases: 1. User change password.
F44 | User login - Bank ID | Users should be able to log in securely with mobile BankID. | - | Not implemented | 1 | Andrew | - | y/n | - | Sofia: Login with mobile BankID is testable, securely needs to be more defined to be testable. Testcase: 1. User logs in with mobile BankID.
F45 | Admin can connect users | An admin should be able to connect users i.e. decide who should be able to chat with who. | - | Not implemented | 1 | Andrew | - | y | - | Linda: Eventuellt ta bort detta krav, beroende på vad RedRiver säger. Sofia: Hur menar kunden här? Konstigt om användare inte kan connecta med varandra själva, utan måste vänta på att admin kopplar ihop en med ens vänner. Testcase: 1. Admin sets up chatroom between two users.
Total No. | 49 |  | Not implemented | 35
|  |  | Started | 2
|  |  | Done | 10

## Usability
ID | Name | Description/User story | Dependencies | Status | Priority Andrew | Priority Linda | Priority Jimmy | Priority Sofia | Priority | Author | Test case | Testable (y/n) | Test case Author | Comments
U1 | Simple UI | The application should have a clear and simple user interface. | U2, U3 | Started | 5 | 5 | 5 | 5 | 5 | Andrew | - | n | - | Sofia: "Clear and simple" is subjective. Customer needs to be more clear. Example testcase: 1. Livestream button creates new livestream.
U2 | WCAG 2.1 | The design should be in accordance with WCAG 2.1 - minimum level AA, better if possible. | - | Started | 5 | 5 | 5 | 5 | 5 | Andrew | - | y | - | Sofia: Customer needs to decide level A, AA or AAA in order for this to be testable. Example testcase: 1. Videos have subtitles.
U3 | UI buttons | The user interface should make use of well-defined buttons based on available actions – for instance writing a new message, taking or uploading a photo, starting a video conversation. | - | Implemented | 5 | 5 | 4 | 5 | 4.75 | Andrew | U.3.1, U.3.2, U.3.3, U.3.4 | y | Sofia | Sofia: Testcases: 1. User wants to chat. 2. User wants to see their friendslist. 3. User wants to make a video call to another user. 4. User wants to start their livestream.
U4 | Responsive | The UI is reponsive and works on mobile and tablet devices. | - | Started | 4 | 5 | 4 | 5 | 4.5 | Andrew | U.4.1, U.4.2, U.4.3, U.4.4 Exploration testing | y | Sofia | Sofia: Testcases: 1. User with android phone. 2. User with android tablet. 3. User with iOS phone. 4. User with iOS tablet.
U5 | App accessibility | The app should be accessible for all users with access to the internet regardless of the device being Android or iOS. | U1 | Started | 4 | 5 | 4 | 5 | 4.5 | Andrew | U.5.1, U.5.2, U.5.3, U.5.4, U.5.5, U.5.6, U.5.7, U.5.8 | y | Sofia | Sofia: Testcases: 1. Application works on online Android device. 2. Application works on online iOS device. 3. Application does not work on offline Android device. 4. Application does not work on offline iOS device.
U6 | UI extents | The full extent of the user interface should be utilized by the user’s ongoing communication. | - | Implemented | 4 | 4 | 4 | 4 | 4 | Andrew | - | unsure | - | Sofia: Example testcases: 1. UI is contained within mobile size without scrolling left/right. 2. UI is contained within tablet size without scrolling left/right.
Total No. | 7 |  | Not implemented | 0
|  |  | Started | 4
|  |  | Done | 2

## Reliability
ID | Name | Description/User story | Dependencies | Status | Priority Andrew | Priority Linda | Priority Jimmy | Priority Sofia | Priority | Author | Test case | Testable (y/n) | Test case Author | Comments
R1 | Environment | The app should work on smartphones and tablets. | - | Implemented | 5 | 5 | 5 | 5 | 5 | Andrew | - | y | - | Sofia: Testcases: 1. Application works on Android tablet device. 2. Application works on Android mobile device. 3. Application works on iOS tablet device. 4. Application works on iOS mobile device. 5. Application works in web browser.
R2 | Harmful code | The system should be protected from harmful code, specifically OWASP Top 10. | S1 | Not implemented | 4 | 5 | 5 | 5 | 4.75 | Sofia | - | y/n | - | Sofia: Depending on what types of attacks we need to be protected from. Example testcases: 1. Application handles CSRF attack. 2. Application handles XSS. 3. Application handles ...
R3 | Consistency | The app should have consistent functionality across all operating systems and environments. | - | Started | 5 | 4 | 4 | 5 | 4.5 | Andrew | - | y | - | Sofia: Testcases: 1. Application works on Android tablet device. 2. Application works on Android mobile device. 3. Application works on iOS tablet device. 4. Application works on iOS mobile device. 5. Application works in web browser.
R4 | Encrypted text on server | All text information stored on server, such as communication logs and personal data, should be encrypted. | - | Implemented | 4 | 5 | 4 | 5 | 4.5 | Linda | - | y | - | Sofia: Testcase: 1. Information on the server is encrypted/unreadable to those who does not have the key.
R5 | Secure text on server | All text information stored on server, such as communication logs and personal data, should be protected from access by third parties. | - | Implemented | 4 | 5 | 4 | 5 | 4.5 | Linda | - | unsure | -
R6 | Secure communication | Communication should take place securely, so that no third party can access transmitted data. | - | Implemented | 4 | 5 | 4 | 4 | 4.25 | Andrew | - | y | - | Jimmy: Use Signal-protocol for fully encrypted communication between users. Investigate possibility to use it in group-chats. Sofia: Testcase: 1. Communication is encrypted/unreadable to those who does not have the key.
R7 | Secure image storage | Images should be stored securely so that no third party has access to them. | - | Started | 4 | 4 | 4 | 4 | 4 | Andrew | - | y | - | Sofia: Vi som grupp måste undersöka hur detta kan göras och därefter lägga till det i kravet. Exempelvis: Images should be stored securely using ... so that no third party has access to them. Andrew: Jag förstår vad du menar här, men jag vet inte om vi måste utforma kravet för att specificera den tekniska lösningen. Sofia: Testcase: 1. Images are encrypted/unreadable to those who does not have the key.
R8 | Virus protection | The system should be protected from viruses - OWASP Top 10 mentioned by customer. | S1 | Not implemented | 4 | 4 | 4 | 4 | 4 | Andrew | - | y/n | - | Jimmy: Uncertain if OWASP Top 10 actually contains "viruses" - really it contains attack vectors. Should this requirement be erased since the customer really means R8? Sofia: Testcase: 1. Application handles virus attacks. What kinds of viruses needs to be explained by customer. We need to check how to handle these kinds of attacks for it to be testable.
R9 | Limited client data storage | As little data as possible should be stored on clients in order to prevent unwarranted spreading of pictures, films and other information. | - | Implemented | 4 | 3 | 3 | 4 | 3.5 | Andrew | - | y | - | Sofia: Testcase: 1. Received pictures are not stored on user device./are stored on server. 2. Received videos are not stored on user device./are stored on server. 3. Received text messages are not stored on user device./are stored on server.
R10 | System backup | All information on system should be backed up in a second location so that it can be restored in case the data in the first location is compromised | - | Not implemented | 3 | 3 | 3 | 3 | 3 | Andrew | - | y/n | - | Sofia: Needs to be divided further. Example testcases: 1. System backup exist for user accounts. 2. System backup exist for chat logs. 3. System backup exist for ...
Total No. | 11 |  | Not implemented | 3
|  |  | Started | 2
|  |  | Done | 5

## Performance
ID | Name | Description/User story | Dependencies | Status | Priority Andrew | Priority Linda | Priority Jimmy | Priority Sofia | Priority | Author | Test case | Testable (y/n) | Test case Author | Comments
P1 | Stress tolerance | The system should accommodate at least 100 simultaneous users (both solely logged in and active) without noticeable detriment to the systems functionality, accessibility or usability. | - | Started | 4 | 4 | 4 | 4 | 4 | Andrew | Automated jMeter tests | y | Andrew | Sofia: Testcase: 1. Stress test with 100 users. 2. Stress test with 1000 users. 3. Stress test with 10000 users.
Total No. | 2 |  | Not implemented | 0
|  |  | Started | 1
|  |  | Done | 0

## Supportability
ID | Name | Description/User story | Dependencies | Status | Priority Andrew | Priority Linda | Priority Jimmy | Priority Sofia | Priority | Author | Test case | Testable (y/n) | Test case Author | Comments
S1 | System protection updates | The system's protection against viruses and harmful code can be updated | R2,R8 | Not implemented | 3 | 3 | 3 | 3 | 3 | Andrew | - | y | - | Sofia: Testcase: 1. Application protection against viruses is updated. 2. Application protection against harmful code (CSRF, XSS etc) is updated.
Total No. | 2 |  | Not implemented | 1
|  |  | Started | 0
|  |  | Done | 0